## Slide 1: Key Project Updates and Recent Construction Activity August 2025 FACFO

## Slide 2: Agenda
State Capital Projects
Energy Improvement Investment
Miscellaneous Repairs/Renovations
Adjacent City Projects

## Slide 3: BBHTC
Schematic Design completed - July 2025
Design Development - Fall 2025
Groundbreaking - Fall 2026
Building utilization – January 2029
Baustert Bahwell Health Technology Center

## Slide 4: NICCS
RFP for Design-Build proposals issued July 2025
Anticipate award Spring 2026
Design and site preparations - Summer 2026
Construction period ~14-16 months
Convocation
Center
Northern Illinois Center for Community Sustainability

## Slide 5: West Plant Boilers
Site clean up ~Sept 2025
Boiler start up ~Nov 2025
Completion ~January 2026

## Slide 6: Energy Improvements
Chart: Schedule Progress ( as reported in May)
| Temp Controls | HVAC upgrades | Solar arrays | Water Conservation | LED Lighting | Building Envelope
% Complete | 21.8 | 34 | 40.67 | 78 | 56.6 | 100
Direct Current Fast Chargers
Stevens Solar

## Slide 7: Lighting Progress
Stevens
LED lighting upgrades to 41 buildings, sports fields, parking lots
- 6 buildings, sports fields, parking to be completed by end summer

## Slide 8: Thermal Storage Progress
Stevens
Convocation Center
Barsema Hall
20 thermal storage tanks
6 thermal storage tanks
Former Jacobs House
East Chiller Plant site prep
60 thermal storage tanks to be constructed

## Slide 9: Solar Progress
Chessick - Fall
Visitor Parking – Spring
Field Arrays – Spring 2026
Stevens - completed
DuSable – in progress

## Slide 10: Roofing
Music & Gabel Hall roofs pending for Fall 2025
DuSable roof complete (pre-solar)
Anderson
~Sep completion
Swen Parson – Oct completion

## Slide 11: Classroom Upgrades
Barsema Hall classroom furniture and technology upgrades

## Slide 12: Relocation/Consolidation
Gender and Sexuality Resource Center relocation to Peters Campus Life

## Slide 13: Mechanical Repairs
Stevenson elevator gear repair

## Slide 14: Electrical Repairs
Emergency generator Automatic Transfer Switch installation
Stevenson main electrical room breaker replacement

## Slide 15: Adjacent City Projects
Kishwaukee Drive Bus Shelter (new)
Pending paving picture
Lucinda/Normal intersection

## Slide 16: Questions?
Solar-powered benches
(phone charging)
Electric maintenance vans